UPMC Pinnacle Memorial Hospital Construction Site Update-June- 2018

Monthly Update

UPMC Pinnacle Memorial Hospital

1701 Innovation Dr.

York, PA 17408

Please see below summary of work taking place at the Pinnacle York Memorial Hospital site:

- The Central Utility Plant steel erection is complete and has been primed.

- Architectural precast panels are being installed.

- Concrete slabs pours are continuing.

- Fireproofing is continuing and moving to the north tower

- Bang-it layout for the MEPs is continuing and duct work is being installed

- Roofing has begun on the West Platform

- Finish site work is continuing: curbs, sidewalk, portions of paving, etc.

- Loucks roadwork is continuing and the road will open back up within the next 2 weeks.

- Roosevelt Avenue is continuing with grading and storm water installation

- 95% of subcontractors have been bought out. Remaining packages are 2nd floor drywall, shades, and fire caulking

- Drywall layout and framing is continuing on the 1st and 3rd floors

Route 30 work will begin within the next few weeks